## Current Iteration
Iteration Number:
|  | Expected Total effort: |  |  |  | 269
|  | Days In Sprint: |  |  |  | 5
Burndown Chart
User Stories |  | Days (Points Completed) |  |  |  |  | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | Task Balance | Percentage Completed
The developer will need to work in SharePoint so the SharePoint needs to be configured for developing the system. | 34 | 8 | 8 | 8 | 6 | 4 | 0 | 100%
Parents, student and staffs will be able to view the offered courses and details about the courses in the system. | 32 | 8 | 8 | 6 | 5 | 5 | 0 | 100%
Parents, student and staffs of the system will be able to view the available research done by the previous student. | 28 | 7 | 6 | 6 | 5 | 4 | 0 | 100%
Parents, student and staffs will be able to view the updated and recent news published in system. | 36 | 8 | 8 | 8 | 7 | 5 | 0 | 100%
Parents, student and staffs will be able to view the success stories of the student who have already graduated from the university. | 27 | 6 | 6 | 6 | 5 | 4 | 0 | 100%
Parents, student and staffs will be able to view the detailed information about the university. | 24 | 6 | 6 | 5 | 4 | 3 | 0 | 100%
Parents, student and staffs will be able to view the contact details of the teachers or administrator of the college from the website. | 30 | 8 | 6 | 6 | 5 | 5 | 0 | 100%
Parents and students shall be able to contact with the administrator regarding any sort of query through the website. | 28 | 6 | 6 | 6 | 6 | 4 | 0 | 100%
The website should have a career option for the users and the students of the college. | 30 | 8 | 6 | 6 | 6 | 4 | 0 | 100%
Effort Remaining | 269 | 204 | 144 | 87 | 38 | 0 | 0 | 100%
Ideal Trend | 269 | 215.2 | 161.4 | 107.6 | 53.8 | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days